## Sheet1
EQUIPMENT PREMOB STATUS AT SPDC APARA 1 LOCATION
S/N | EQUIPMENT | SERIAL NR | PREMOB REQUIREMENTS | PREMOB STATUS
1 | POWER PACK 1 | 6TB17953 | - | Premobbed. Stickers on location
2 | POWER PACK 2 | 6TB17947 | - | Premobbed. Stickers on location
3 | MUD PUMP 1 | 3ER11239 | - | Premobbed. Stickers on location
4 | MUD PUMP 2 | 3ER09709 | - | Premobbed. Stickers on location
5 | CENTRIFUGAL PUMP 1 | 8822718 | - | Premobbed. Stickers on location
6 | CENTRIFUGAL PUMP2 | 8797523 | - | Requires Premobbing
7 | WELDING MACHINE | 5468606 | 1) Spark Arrestors | Requires Premobbing
8 | FORKLIFT | ABC331XE | 1) Electrical fork adjuster failed | Requires Premobbing
2) TD Ram Seal Leakage
3) Replacement of work light bulbs
4) Modification of the front right trafficator
5) Certification of Lifting max/welded position
9 | CRANE | XA786LEH | 1) Replacement of LMI (Load indicator) | Requires Premobbing
2) Replacement of bulb
3) First Aid Box
4) Leaking out rigger hoses to be fixed.
10 | HILUX 1 | APP154BG | 1) No First Aid Box | Requires Premobbing
2) No road safety reflective stickers
11 | HILUX 2 | APP153BG | 1) No First Aid Box | Requires Premobbing
2) No road safety reflective stickers
12 | BUS 1 | JJJ94AE | 1) No breaks. | Requires Premobbing
2) No Hand break
3) No First Aid box
4) No spare tire
5) Rear bumper needs to be worked on
6) Air freshner required
7) Fenders need panel beating
13 | BUS 2
14 | AMBULANCE | JJJ84AW | 1) No Hand break | Requires Premobbing
2) 7 New Tires required
3) 230V Socket not working
4) A/C not working
5) First Aid Box empty
6) Oxygen cylinder need to be clamped
7) Air freshner needed
15 | GENERATOR 1 | 0269525/022 | - | Premobbed. Stickers on location
16 | GENERATOR 2 | 1447491 |  | Requires Premobbing
17 | HYDRANT CP | 8851914 |  | Requires Premobbing